Contents

Strategic Objective 1

An accessible complaints process with trusted outcomes

| Actions specified in the Strategic Plan | Due date |
| --- | --- |
| 1 – Accessibility (A) |
| a | Develop, test and launch an online form for submitting complaints | 2018/19 (NB: 2017/18 in StratPlan) |

| 2 – Case Management (B) |
| --- |
| a | Replace the Case Management System (CMS) (costs cover all four years) | 2019/20 |
|  | i | Complete tender process and appoint supplier | April 2018 |
|  | ii | Funding approval | TBC |
|  | iii | Develop the CMS with the successful contracted supplier | TBC following funding approval |
|  | iv | Test the CMS |  |
|  | v | Staff training |  |
|  | vi | Implement the CMS |  |

| 3 – User Experience (C) |
| --- |
| a | Prepare and publish service standards | 2018/19 (NB: 2017/18 in StratPlan) |
|  | i | Publish service standards on new website | December 2018 |
| b | Explore options for recording levels of complaint satisfaction | 2018/19 (NB: 2017/18 in StratPlan) |

| 4 – Remit (D) |
| --- |
| a | Prepare for registration of interests of MSPs and introduction of a lobbying register | 2019/20 |
|  | i | Prepare for investigation of complaints about lobbying | 2018/16 |
|  |  | Finalise Investigation Procedures and related documentation | May 2018 |
|  |  | Implement Procedures | May 2018 |
|  |  | Conclude a Memorandum of Agreement with the Clerk to the Parliament and with the Procurator Fiscal | May 2018 |

| Performance measures | Due date |
| --- | --- |
| Complaints against councillors and members of public bodies |
| 1 | Numbers of complaints and cases received | Collated / reviewed monthly and published in Annual Report |
| 2 | Categories and originators of complaints |  |
| 3 | Numbers of complaints and cases completed |  |
| 4 | Outcome of complaints and cases |  |
| 5 | Decisions following a public hearing held by the SCS. |  |
| 6 | Performance against targets for initial assessment and for completion of investigations |  |
| Complaints against MSPs |
| 6 | Numbers and categories of complaints | Collated / reviewed monthly and published in Annual Report |
| 7 | Numbers proceeding and time taken for admissibility and investigation stages |  |

| Annual Actions | Due Date |
| --- | --- |
| 1 | Review Initial Office Assessment (IOA) process and associated standard documents | June 2018 |
| 2 | Review and merge complaint leaflet and prepare Investigations Procedures for MSP complaints | May 2018 |
| 3 | Remove web summaries and develop web notes | April 2018 then ongoing |
| 4 | Review web materials to be transferred to redesigned website | June to September 2018 |

Strategic Objective 2

Public boards which are effective, and reflective of society

| Actions Specified in the Strategic Plan | Due Date |
| --- | --- |
| 1 – Scottish Government Public Boards Governance and Diversity Improvement |
| a | Continue to work with officials in the Scottish Government to develop, co-ordinate and implement actions to improve on board diversity and thereby enhance board governance. | 2018/19 |
|  | i | Use the Driver Diagram agreed with SG officials in 2016/17 to develop a new action plan based on the current draft and work in partnership with officials to implement agreed actions in the plan that are appropriate for the Commissioner’s staff and/or PAAs to fulfil. Key actions already identified and brought forward include: | August 2018 then ongoing |
|  |  | Working with officials and boards on outreach and positive action measures such as training people from underrepresented groups to increase their chances of applying successfully | Ongoing minimum 2 per annum |
|  |  | Reporting the results of the revised applicant survey | September 2018 (NB content will not be available for the 2017/18 annual report) |
|  |  | Reporting stage one findings of the research project with the intent of assessing in due course the impact that more diverse appointments are having on board governance and commence stage two of the research. | May 2018 |
|  |  | Report on stage two findings. | February 2019 |
|  |  | Commence stage three of the research. | September 2018 |
|  |  | Commence stage four of the research (qualitative). | October 2018 |
|  | ii | New actions include: |  |
|  |  | Running, along with officials, a mentoring scheme with the purpose of developing current members from underrepresented groups to become chairs in the future. Assessing scheme effectiveness. | Ongoing |
|  |  | Working with officials to develop a plan of action specifically intended to redress underrepresentation of disabled people. | July 2018 |
|  |  | Working with officials to develop a plan of action specifically intended to redress underrepresentation of people under the age of 50. | September 2018 |

| 2 – Partnership Approach (E) |
| --- |
| a | Continue to work in partnership with the Scottish Government public appointments team to implement the agreed approach to forward planning. (costs cover all four years) | 2019/20 |
|  | i | Working with officials to enhance strategic planning for appointment activity by allocating PAAs at the long term strategic planning stage before appointment rounds are agreed and in train | 2018/19 |
|  | ii | Run joint SG and PAAs as well as PAAs only Communications Days to train on new developments in public appointments. | Four per annum |

| 3 – Review of 2013 Code (F) |
| --- |
| a | Conduct a full review of the effectiveness of the 2013 Code during the period of this plan (costs allocated to 2016/17, 2018/19 and 2019/20) | 2019/20 |
|  | i | Conduct stage 3 of the thematic review of the 2013 Code’s operation. This will be a review of progress against the recommendations made in the report on stage 2 of the thematic review. Initial scope for this will include: | 2017/18 |
|  |  | Report on the effectiveness of the lessons learned process | August 2018 |
|  |  | Report on board succession planning | July 2018 |
|  |  | Stage one report on the impact of diversity on board governance | May 2018 |

| Performance measures | Due Date |
| --- | --- |
| 1 | Numbers of regulated bodies and posts | Published in Annual Report |
| 2 | Number of appointment rounds initiated and completed |  |
| 3 | Number of applications and appointments |  |
| 4 | Time taken for individual stages of appointment rounds |  |
| 5 | Timing of re-appointments |  |
| 6 | Numbers of people appointed who have not previously held and do not currently hold a regulated appointment |  |
| 7 | Satisfaction levels with appointment process |  |
| 8 | Changes in demographic profile of applicants, appointees and board membership |  |
| 9 | Performance against Diversity Delivers targets |  |

| Annual Actions | Due Date |
| --- | --- |
| 1 | Conduct annual SLA discussion with each PAA to discuss contribution to appointment round, training needs and trends | Sep/Oct and Jan to Mar |
| 2 | Provide training for panel members if/when requested | As required |
| 3 | Post case studies of examples of successful new approaches on website. | When PAAs advise round is appropriate for study |
| 4 | Write new content for and transfer a proportion of the existing content from the old to the new website. | TBC according to agreed timetable |
| 5 | Prepare a briefing for the new Commissioner on the public appointments system. | March 2019 |
| 6 | Amend guidance on the Code and potentially the Code itself to take account of changes made to public appointments following enactment of the Gender Representation on Public Boards (Scotland) Act 2018 | September 2018 |
| 7 | Provide briefings to SG officials and parliamentary clerks/committees on the regulated public appointments process and in particular on cases in which appointments are subject to parliamentary approval. | Ongoing |
| 8 | Provide training for Scottish Government Graduate Development Programme/Fast-streamers on CESPLS regulation of public appointments. | Once per annum date TBC |
| 9 | Provide training for independent panel members on their role and responsibilities under the Code. | One group session per annum date TBC |
| 10 | Draft “Diversity Delivers – Ten Years On” for publication. | November 2018 |
| 11 | Revise public appointments records and records management procedures to respond to the results of the GDPR data audit. |  |
|  | i | Prepare project plan | June 2018 |
|  | ii | Complete actions | TBC |

Managing resources

| Actions Specified in the Strategic Plan | Due Date |
| --- | --- |
| 1 – Budget Limits |  |
| a | manage expenditure within the budget limits agreed annually with the SPCB | Annually |
|  | i | Provide regular financial reports to the Management Team. | Monthly |
|  | ii | Review the business plan and consider budget pressures | Bi-monthly |

| 2 – Key Resource |  |
| --- | --- |
| a | find ways of maintaining and where possible improving job satisfaction and performance | Ongoing |
|  | i | Ensure that staff policies and terms and conditions reflect current legislation and good practice. | Annually |
|  |  | Develop a policy review project plan | April 2018 |
|  |  | Identify key policies for early review | April 2018 |
|  |  | Develop revised policy review procedures | June 2018 |
|  |  | Agree policy review schedule | June 2018 |
|  |  | Review identified policies | July onwards |

| 3 – Communication |  |
| --- | --- |
| a | maintain good channels of communication with the SPCB, committees of the Parliament, Ministers, officials of the Scottish Government and public bodies and to work in partnership wherever possible. | Ongoing |
|  | i | Offer subject matter induction meetings to all new Clerks to relevant committees | Ongoing |
|  | ii | Continue membership of specialist subject-related groups. For example, the Scottish Information Commissioner’s Part 7 Network Group. | Ongoing |
|  | iii | Engage with parliamentary committees in relation to relevant subject enquiries and the annual report. | Ongoing |

| 4 – Website (G) |  |
| --- | --- |
| a | review and where appropriate improve the accessibility, clarity, consistency and ease of use of the website. | 2018/19 |
|  | i | Agree project plan for redevelopment of website. | March 2018 |
|  | ii | Project immersion phase completed | May 2018 |
|  | iii | Development of website information architecture | May 2018 |
|  | iv | Revised visual identity agreed | June 2018 |
|  | v | Wireframes approved | July 2018 |
|  | vi | Website visual design approved | September 2018 |
|  | vii | Content development | June to September 2018 |
|  | viii | Functional specification agreed | October 2018 |
|  | ix | Training | November 2018 |
|  | x | Launch new website | November 2018 |

| Performance measures | Due Date |
| --- | --- |
| 1 | Performance against budget and annual business plan targets | Monthly and published in Annual Report |

| Annual Actions | Due Date |
| --- | --- |
| 1 | Develop a Memorandum of Understanding with the National Records of Scotland for the transfer of archive records. | September 2018 |
| 2 | Agree a Framework Agreement with the Scottish Parliamentary Corporate Body. | Driven by the SPCB |
| 3 | Identify key risks to the business, ensure mitigating actions are in place and review regularly | Ongoing |
|  | i | Identify risks and mitigating actions for 2018-19 | April 2018 |
|  | ii | Review risks | Bi-monthly |
| 4 | Publish the annual report and accounts for 2017-18. A new visual identity will be incorporated but content will utilise the current ‘accounts’ format for a further year. | October 2018 |
| 5 | Prepare a budget for 2018/19 | August 2018 |
| 6 | Draft the business plan for 2018/19 | February 2018 |
| 7 | Review the Commissioner’s Publication Scheme and Guide to Information | August 2018 |
| 8 | Review the Commissioner’s Records Management Plan | June and December 2018 |
| 9 | Prepare for the introduction of the General Data Protection Regulations | May 2018 |
| 10 | Appoint a Data Protection Officer | May 2018 |
| 11 | In concert with the SPCB and Officeholders, finalise and then implement the actions set out in the CESPLS British Sign Language action plan. | July 2018 then ongoing |
| 12 | Review Investigating Officer complement and structure | October 2018 |
| 13 | Prepare for the appointment of a new Commissioner | March 2019 |

# Text boxes

|  | Commissioner for Ethical Standards in Public Life in Scotland |
| --- | --- |

Annual Business Plan

2018/19