## Sheet1
Ref. | Assigned to | Documents Required | Status | 2021-04-30 | 2021-05-31 | 2021-06-01 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-30 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-20 | 2022-06-30 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31
Staff and resources
S1 |  | We will aim to ensure that we have the staff required with the relevant skills, knowledge, experience and values to acquit our functions; we will review our current structure and staffing arrangements and identify those areas that require to be revised in order for us to work most effectively
i |  | Fill all vacancies currently being carried as a matter of priority. Include increased capacity to support SMT and rise in investigatory work for MSP and councillor complaints.
ii | AO | Draft business case for SPCB to cover: Additional IO post, Additional CSO post, Full time hours for PAO post | Completed
Case drafted
Case agreed
iii | AESC/SIO | Recruit to IO posts | Completed
Two IO vacancies filled
An additional IO appointed
iv | AESC | Cover for PAM role as currently fulfiling role of AESC as well as MSP complaint handling | Completed
PAO temporary promotion to PAM role for one year
v | AESC/PAM | Backfill PAO role thorugh recruitment, secondment or agency | Assigned
|  | PAO appointed for one year | [6 empty] | Unable to fill via recruitment or secondment due to uncertainty over ESC return date or ESC appointment date. This remains the position at March 2022. C/F
vi | AESC/AO | Recruit to additional CSO post to provide support for AESC and SMT | Completed
CSO appointed
vii | AO/SIO/PAM | Induct all new staff into their roles | Completed
Induction successfully completed
viii | AESC/SMT | Complete draft action plans for all activity for next two years based on biennial business plan – map staff/resources/available skillsets to all activities Staff members and teams mapped to individual actions – ensure resilience/double cover as failsafe for staff departures and/or incapacity | Completed
Action plans drafted for two years completed
|  | Actions mapped to avaliable staff, building in resilience and cross-office working | [7 empty] | Note - further workforce planning required at end March due to workload and available resources. All activity currently planned is mapped to available staff at March 2022.
|  | Assess operational efficiency of new staff complement against office needs at time and for future | Assigned
Assessment conducted
|  | Reassess office needs to produce a final workforce plan | Assigned
|  | Final workforce plan produced | [13 empty] | AESC has asked SMT to bring this work forward to March/April due to increased workload and limited capacity as well as parliamentary and public interest in the work of the office.
ix | AESC/SMT | Performance reviews conducted for all staff and actions for year ahead agreed | Completed
All staff introduced to linkages between strategic business and action plans as well as financial implications of activities
Performance reviews conducted and individual action plans agreed
S2 |  | We will aim to ensure that all staff are trained and developed to fulfil their roles effectively, including on the revised Codes of Conduct for Councillors and Members of Public Bodies, good practice in complaint handling and equality diversity and inclusion in all of our practices
i | AESC/SMT | Formal training and development plans to be agreed with all staff in order for them to meet their individual objectives (see S1). Highlighted training includes presentation at hearings, management and governance, MSP complaint-handling, health, safety and wellbeing risk assessments, investigating complaints of harassment, Plain English and attention to detail. Incorporates C4i. | Assigned | [10 empty] | Thus far, all relevant staff have received training in presentation at hearings, management and governance, MSP and other complaint-handling (investigatory staff), supporting people party to harassment complaints, handling complaints about us, Plain English and attention to detail.
Plans agreed for current staff
Plans agreed for new staff following probationary period
ii | AESC/AO/SMT | Training secured from relevant sources | Completed
|  | Appropriate training researched, costed and obtained | [13 empty] | Training was secured and run in March and April on sexual harassment investigations and EDI with a focus on trans issues.
iii | AESC/SMT | Training rolled out | Completed
|  | Staff trained to fulfil role with individual and office-wide records maintained | [10 empty] | See S2
S3 |  | We will regularly survey staff and act on the results of such surveys with a view to ensuring their wellbeing | [11 empty] | Flexible working preferences survey conducted. Views on organisation and wellbeing levels surveys still to be designed and run as at March 2022.
i | PAM | Surveys designed to cover: flexible working preferences, views on the organisation, wellbeing levels | Assigned
Surveys designed - flexible working
Surveys designed
SMT agree content - flexible working
SMT agree content
Surveys finalised - flexible working
Surveys finalised
ii | AESC/SMT | Survey results reviewed at SMT meetings | Assigned
Conclusions drawn - flexible working
Conclusions drawn
Practices revised - flexible working
Practices revised
S4 |  | We will introduce a suite of new and revised policies that have staff wellbeing at their heart. We will ensure that staff are trained to fulfil their role in a way that is respectful of all indivduals who contact us, regardless of their backgrounds | Completed
|  | All staff introduced to and consulted on our values as an office to ensure understanding of and adhereance to these in all of our work | Completed
Staff introduced to values
Staff asked to provide views in formal and informal settings
Staff demonstrate understanding of and adherence to our values
i | PAO/AESC/SMT | All HR related policies revised or updated to take account of our revised operational context (including pandemic) and to secure staff wellbeing | Completed
|  | Suite of draft policies produced alongside reasons for introduction of new policies or amended existing ones | Completed
ii | PAO | Staff consulted on all policies | Completed
Policies issued for views
iii | PAM | Revised policies in place | Completed
Results of consultation fed back to staff
Policies introduced
Policies published
iv | AO/SIO | Secure confidential counselling services for staff who wish to use them | Completed
Confidential counsellng service in place
Staff provided with means to access service
MSP , Councillor and Public Body Complaints
C1 |  | We will consult all relevant stakeholders on our current complaint handling procedures and revise them and publish them in the form of an investigations manual which takes account of the views received. Parts of the manual will be produced in Easy Read, BSL and other languages to ensure accessibility | Assigned
C2 |  | We will adapt our procedures to take account of stakeholder views and engender trust in the way that we work
i | AESC/SIO | Upgrading and updating of procedural documentation (templates, factsheets, flowcharts, checklists etc) for MSP, councillor and board member complaint handling | Assigned
Interim changes to admissibility forms to be agreed with Standards Commission as a starting point (urgent)
Template letters revised to align with organisation's values (urgent)
|  | All documentation updated, adopted and published, in the form of a draft investigations manual for consultation | [10 empty] | Draft manual at V5 at year end.
ii | SIO/IOs | Adopt new procedures for interim period | Completed
Procedures adopted and staff trained on use
iii | SIO | Issue manual to key stakeholders for comment | Assigned
|  | Draft manual published on website | [9 empty] | Draft manual at V5 at year end. Deadline for production extended by AESC.
|  | Stakeholder views invited | [10 empty] | Draft manual at V5 at year end. Deadline for production extended by AESC.
|  | Responses incorporated | [11 empty] | Draft manual at V5 at year end. Deadline for production extended by AESC.
iv | AESC/SIO | Develop an action plan documenting an appropriate suite of arrangements in anticipation of amending legislation (sexual misconduct plus removal of the time bar) coming into force | Completed
Initial liaison with relevant parties
Development of outline proposal
|  | SPCB interaction as necessary | [7 empty] | Revised to parliamentary interaction in relation to support for parties to complaints of this nature. AESC highlighted with SP in October. No substantive response received at the year end.
i | AESC | Map key stakeholders | Completed
Full list of stakholders established
ii | AESC | Make initial informal contact | Completed
Initial discussions conducted by way of remote meetings
iii | AESC | Contact formally by way of introduction ot AESC and plans for office | Completed
Email to all stakeholders with copy of strategic plan
iv | AESC/SIO | Consultation with key stakeholders on prospective changes | Completed
Stakeholder views collated and analysed
v | AESC | Stakeholder view lead to adaptation and adoption of final revised strategic plan | Completed
Views on broad proposals incorporated into revised strategic plan
Reasons for adoption or rejection of suggested changes recorded
C3 |  | We will pubish our procedures as revised so that everyone knows what to expect
i | SIO | Publish revised investigations manual | Assigned | [11 empty] | Draft manual at V5 at end Feb 2022. Deadline for production extended by AESC. Final consultation version should be published by end March 2022. Revised date for incorporation of responses TBC
ii | HCS/CST | Have parts of manual that are of interest and relevance to the public translated into BSL, Easy Read and other languages
Public Appointments
A1 |  | We will publish for consultation a draft revised Code of Practice for appointments with a greater focus on outcomes, accountability and transparency and an emphasis on learning lessons | Completed
i | AESC/PAM | Publish analysis of consultation responses on prospective Code of Practice revisions alongside a draft of the revised Code for consulation | Completed
Lay draft and consult Scottish Ministers, Scottish Parliament and key stakeholders on proposals from July 21-Sept 21
|  | Analyse responses by November 2021 | [9 empty] | Deadline extended for further consultation with SG. Analysis completed in February 2022.
A2 |  | We will take account of all stakeholder views in order to finalise the Code
i | AESC | Publish results of analysis | Completed
|  | Results published and provided to all stakeholders | [9 empty] | Deadline extended for further consultation with SG. Analysis completed in February 2022. Publication delayed until March 2022.
ii | AESC | Introduce revised Code | Assigned
|  | Publish and provide to Scottish Parliament | [10 empty] | Deadline extended for further consultation with SG. Analysis completed in February 2022. Publication delayed until March 2022.
iii | HCS/CST | Have parts of Code that are of interest and relevance to the public translated into BSL, Easy Read and other languages
A3 |  | We will provide guidance and support to everyone engaged in the appointments process with a view to their implementing the new Code's provisions effectively
i | AESC/PAM | Draft statutory guidance | Assigned
|  | Publish | [12 empty] | Deadline for Code extended for further consultation with SG. Guidance publication delayed until March 2022
ii | AESC/PAM | Run training for PAAs, PAT and panels on new Code's application | Assigned | [11 empty] | Now scheduled for spring and summer of 2022 - C/F
iii | AESC | New Code comes into effect | Assigned | [13 empty] | Now scheduled for autumn 2022 - c/f in consultation with SG
Continual training and guidance developed to support revised Code
Committee engagement on transparency and reporting
iv | APAM | Continue to feed into lessons learned for the Scottish Government by running applicant surveys on a round by round basis and providing reports of feedback, whenever a request to run a survey is made | Completed
|  | Reports produced after appointment rounds |  |  |  | Ongoing
A4 |  | We will seek support to revise and republish Diversity Delivers to include new recommendations for the achievement of greater board diversity | Completed
i | AESC | Consult informally from September 2021
ii | AESC | Issue formal request October 2021
| AESC/PAM | Commence research into good practice and what the content of the revised strategy should include
Governance and Accountability
G1 |  | We will put new and more effective governance measures in place, inclusive of independent elements, to ensure for ourselves and to assure others, by way of public reporting, that we are achieving our objectives in line with our purpose and our values and in line with the resources made available to us
i | AESC/SMT | Full review of governance arrangements | Assigned
|  | Appointment of internal auditor | [7 empty] | Appointment delayed as Section 22 Report not published until Dec 2021
|  | Review of Advisory Audit Board remit and membership | [6 empty] | AAO provided paper to AAB on governance considerations in May 2021. Discussions on this, including how and the extent to which the SPCB may be involved, are ongoing as at March 2022.
|  | Review of whistle-blowing policy | [8 empty] | Policy was updated following staff consultation in June 2021. Further review depends on establishment of reporting routes when concerns about ESC
ii | AESC/AO | Assess external arrangements folllowing publication of wider scope review report and recommendations | Assigned
|  | Engage with SPCB and parliamentary commitees | [9 empty] | SPCB infomal engagement began by due date. Formal engagement commenced in Feb 2022 due to delayed s 22 report. Still ongoing at March 2022. AESC gave evidence to SPPA Committee in Feb 2022 and Local Govt, Housing and Planning Cttee in March 2022
|  | adopt reciprocal measures | [13 empty] | See entry immediately above. O/S at year end - C/F
iii | AESC/SMT | Re-establish SMT meetings | Completed
Re-establish meetings and standard agenda items
|  | Agree adendas for year ahead to cover off additional items in policies etc. | [6 empty] | Delayed to Nov 2021
Publish minutes
|  | Consider meeting publicly on quarterly basis | [10 empty] | Delayed to Jan 2022
iv | AESC/AO | Revert to prior arrangements for risk assessment - updated to reflect the fact that substantive risks to ESC's operation were not identified and addressed | Completed
Adopt risk management policy
Populate risk register
Include risk as item for SMT quarterly meetings
Consult AAB and internal auditors on arrangements on an ongoing basis
v | AESC/SIO | Commission an external independent review of all decisions made on complaints from August 2020. Report on findings | Assigned
|  | Seek approval for contingency funding for review | [13 empty] | Discussions with SPCB on issue began formally in February 2022 and are ongoing. O/S at year end - C/F
|  | Commission review | [13 empty] | Discussions with SPCB on issue began formally in February 2022 and are ongoing. O/S at year end - C/F
|  | Report on findings | [13 empty] | Discussions with SPCB on issue began formally in February 2022 and are ongoing. O/S at year end - C/F
vi | AESC/AO | Review current schemes of delegation and revise to address contingencies such as avaliability of ESC/AESC to make decisions | Assigned
Review scheme of delegation and identify areas where ESC/AESC authority required
Put alternatives in place to deal with contingency of no ESC/AESC avaliability to make decisions
vii | AESC/SMT/SPCB | Consider whether standing orders can be revised to ensure collaborative decision making between ESC/SMT and wider organisation and preclude management override of controls | Assigned
|  | Revise standing orders to give SMT a clear governance role set out in terms of reference for ESC and SMT members | [14 empty] | See above at G1 v. re discussions with SPCB. O/S at year end - C/F
|  | Ensure ESC bound by SMT decisions in legislation and/or by some other contractual means | [14 empty] | See above at G1 v. re discussions with SPCB. O/S at year end - C/F
viii | AO/AESC/SMT | Review and formalise the budget process to ensure formal approval obtained from SMT as a whole on an annual rolling basis including recommending the budget for submission to the SPCB | Completed
Review and revise current budget process
Agree revised process with SMT
Schedule consideration of budget against agreed business plan annually
ix | AESC/AO | Prepare a medium-term financial plan to include alternative scenarios of expected income and expenditure in future years, associated assumptions for each scenario and quantifying the funding gaps. Take account of the impact of leaving the EU, the Covid-19 pandemic and other expected changes | Assigned
Scan horison for range of scenarios and their potential impact on ESC operation
Quantify potential impact of each on avaliable resources
Draft financial plan showing variances by senario(s) and their potential impact on the office's ability to fulfil its functions
G2 |  | We wil adopt quality assurance monitoring of key performance indicators, such as timescales for investigation stages, including surveys of the views of those with whom we come into contact, and report publicly on the results. We will use those results to improve on what we do and ensure our practices are equitable
i | SIO | Draft performance management framework. Reintroduce previous KPIs and consult on these and other new ones to track progress of investigatory work. | Assigned
|  | Reintroduce prior KPIs by reference to annual reports | [13 empty] | O/S at year end pending consultation on the investigations manual - C/F
|  | Design new KPIs related to stakeholder views on our performance | [13 empty] | O/S at year end pending consultation on the investigations manual - C/F
|  | Consult stakeholders on appropriateness and relevance | [13 empty] | O/S at year end pending consultation on the investigations manual - C/F
|  | Analyse responses and adapt KPIs as appropriate | [13 empty] | O/S at year end pending consultation on the investigations manual - C/F
ii | PAM/SIO | Include a survey that both complainers and respondents can complete on an anonymous basis to give views on how we investigate complaints | Assigned
Design and roll out survey
Set baseline based on initial results
iii | SIO/SMT | Previous KPIs and new ones adopted and published | Assigned
Adopt KPIs
Put tracking measures in place and assess for eficacy/accuracy
Report on progress internally against KPIs quarterly and externally annually
iv | AO/SIO | Ensure statistics for previous two years are accurate and comparable with those produced under previous ESC | Completed
Statistics verified internally and produced for inclusion in annual report and accounts for 2021/22
G3 |  | We will report publicly on the difference that the new Code of Practice is making to the appointments process, for good or bad, with a view to improving on practices. We will do so by publicising instances of good practice or innovative practice and learning as well as areas for improvement
i | AESC | Engage with the Scottish Parliament's subject committee about appointments practices with a view to making improvements and increasing transparency | Assigned
|  | Agree suitable reporting arrangements |  |  | Discussions commenced with SPPAC clerks from May onwards and the Cttee's views were also sought in relation to Code revisions. These will continue, including on reporting - C/F
|  | Submmit periodic reports | [17 empty] | See above as well as Code consultation analysis and revised Code. O/S at year end - C/F
ii. | APAM | Publish good practice case studies on website | Assigned
G4 |  | We will work in partnership with the Scoittish Government, the Scottish Parliament, the Standards Commission for Scotland and other stakeholders to promote good practice and to ensure that lessons are learned from the outcomes of our investigations. Our ongoing engagement with our stakeholders will be regular and meaningful.
i. | AESC/SMT | Meaningful re-engagement the Scottish Ministers, MSPs, public body board members, local authority councillors, monitoring officers and representative organisations such as COSLA, SOLAR and SOLACE to inform and shape our work and our performance |  | Talks initiated in April and have been ongoing (refer to SMT minutes for detail).
Other Corporate activity
O1 |  | We recognise that public sector resources are limited and understand that we must review, scrutinise and report publicly on our work to ensure best value and continous improvement
i | AESC/SMT | Draft strategic plan for 2021-24 | Completed
Draft plan
Seek formal/informal feedback from staff and stakeholders
Redraft based on feedback
Incorporate wider scope review
Publish for formal consultation
ii | AESC/AO | Draft biennial business plan for 2021-23 | Completed
Draft plan
Revise plan to take account of responses to strategic plan
|  | Schedule annual consideration of biennial plan on an ongoing basis | [10 empty] | Delayed until March 2022
iii | HCS | Annual Report and Accounts design formatting and online presentation project | Completed
Finalise online ARA template
iv | AESC/SMT | Decision on office accomodation needs | Completed
Finalise extension of MoTO
v | AESC/HCS | Review contractual arrangements for CMS | Completed
Finalise contract extension
vi | AESC/SMT | Develop plan for exit of Covid-19 lockdown restrictions and implement lockdown exit plan | Assigned
|  | Plan developed | [8 empty] | All planning has been done in the course of SMT meetings and has followed SG guidance and in consultation with staff (see SMT minutes and all staff meeting minutes for detail).
|  | Plan implemented | [8 empty] | All planning has been done in the course of SMT meetings and has followed SG guidance and in consultation with staff (see SMT minutes and all staff meeting minutes for detail).
vii | AO | Risk assessment of EU exit on current and future activities | Completed
|  | Update previous risk assessment | [5 empty] | Not done at year end in that previous PESTL analysis not updated - C/F
|  | Feed potential impacts into budget projections | [13 empty] | Based on previous projections
viii | HCS | Review of records management arrangements in prepartion for resubmission of our RMP to NRS | Assigned
See RMP Review Project Plan
ix | AO/PAM | Review and revise all outstanding policies that are currently beyond their published review date | Assigned
Review policies
Update as appropriate
Publish as updated
x | AO | Review entire website to ensure up to date | Assigned
|  | Assess all pages | [13 empty] | Review underway at March 2022. Not completed at year end
|  | Address broken links | [13 empty] | Review underway at March 2022. Not completed at year end
|  | Remove or update outdated items | [13 empty] | Review underway at March 2022. Not completed at year end
|  | Assess material published against publication scheme | [13 empty] | Review underway at March 2022. Not completed at year end
xi | AESC/SMT | Prepare for publication of wider scope review report | Assigned
Respond formally to findings
Prepare lines for media and stakeholder enquiries
|  | Prepare for prospective committee appearance | [8 empty] | AESC gave evidence to SPPA Committee in Feb 2022. C/F other sessions into 2022/23
|  | Implement agreed recommendations | [8 empty] | See above for progress against all recommendations. Some to C/F at year end.
Note on AK95: Angela Glen: Potentially public consultation end of Apr 22, incorporate responses end of May 22?