## Sheet1
Ref. | Assigned to | Actions | Status | Strategic Objective (as per Plan) | 2022-04-30 | 2022-05-30 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-30 | 2023-06-30 | 2023-07-30 | 2023-08-30 | 2023-09-30 | 2023-10-30 | 2023-11-30 | 2023-12-30 | 2024-01-30 | 2024-02-29 | 2024-03-30 | 2024/25
Staff and resources
S1 |  | We will aim to ensure that we have the staff required with the relevant skills, knowledge, experience and values to acquit our functions; we will review our current structure and staffing arrangements and identify those areas that require to be revised in order for us to work most effectively |  | Expanded from SO intro para; new SO?
i | AESC/SMT | Conduct workforce planning covering all sections of the office. Include increased capacity to support the AESC/ESC the SMT and the rise in investigatory work for MSP and councillor complaints.
ii | AESC/AO | Draft business case for SPCB to cover all additional posts required following workforce planning. | Assigned
Final workforce plan produced
Final workforce plan agreed
Case for SPCB drafted and submitted
Case agreed
iii | AESC/SIO | Recruit to additional posts | Assigned
All new vacancies filled
iv | AESC/AO | Recruit to fill pre-existing vacancies | Assigned
Recruit CSO (subject to workforce planning)
Recruit PAO
CSO appointed
PAO appointed
v | AO/SIO/PAM | Induct all new staff into their roles | Assigned
Induction of PAO successfully completed
Assig individual actions and idenitfy training required at end of PAO probationary period
Induction new staff successfully completed
Assign individual actions and idenitfy training required at end of new staff probationary period
vi | AESC/SMT | Prepare action plans for all activity for next two years based on biennial business plan – map staff/resources/available skillsets to all activities. Staff members and teams mapped to individual actions – ensure resilience/double cover as failsafe for staff departures and/or incapacity. | Assigned
Action plans for each function for next two years prepared
Actions mapped to available staff, building in resilience and cross-office working
Build resilience in teams by rotating staff around different office functions
vii | AESC/SMT | Assess operational efficiency of new staff complement against office needs at time and for future | Assigned
Assessment conducted
viii | AESC/SMT | Report on outcome of workforce plan implementation | Assigned
Report produced
ix | AESC/SMT | Actions assigned to each section and staff member | Assigned
All staff reminded of linkages between strategic business and action plans, risks to achievement as well as financial implications of activities
Individual action plans agreed
S2 |  | We will aim to ensure that all staff are trained and developed to fulfil their roles effectively, including on the revised Codes of Conduct for Councillors and Members of Public Bodies, good practice in complaint handling and equality diversity and inclusion in all of our practices |  | SO1d
i | AESC/SMT | Performance reviews conducted for all staff and actions for year ahead agreed | Assigned |  | Throughout year on anniversary of appointment. All reviews complete by end of FY.
Formal training and development plans to be agreed with all staff in order for them to meet their individual objectives (see S1). Highlighted training includes health, safety and wellbeing risk assessments, Equality, Diversity and Inclusion and mitigating biases.
ii | AESC/AO/SMT | Organisation wide training requirement identified and suppliers sourced | Assigned
Appropriate training researched, costed and obtained
S3 |  | We will regularly survey staff and act on the results of such surveys with a view to ensuring their wellbeing |  | Expanded from SO intro para; new SO?
i | PAM | Surveys designed to cover: flexible working preferences, views on the organisation, wellbeing levels | Assigned
Surveys designed to collect views on the organisation and wellbeing levels
SMT agree content
Surveys finalised - views on the organisation and wellbeing levels
ii | AESC/SMT | Survey results reviewed at SMT meetings | Assigned
Conclusions drawn
Practices revised
S4 |  | We will ensure that HR-related our policies have staff wellbeing at their heart. We will ensure that staff are trained to fulfil their role in a way that is respectful of all indivduals who contact us, regardless of their backgrounds | Assigned | Expanded from SO intro para; new SO?
i | AESC/SMT | All staff introduced to our values as an office to ensure understanding of and adherence to these in all of our work | Assigned |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Staff introduced to values
Staff asked to provide views in formal and informal settings
Staff demonstrate understanding of and adherence to our values
Develop and document method for review, staff consulation, training and comms.
MSP , Councillor and Public Body Complaints
C1 |  | We will consult all relevant stakeholders on our current complaint handling procedures and revise them and publish them in the form of an investigations manual which takes account of the views received. Parts of the manual will be produced in Easy Read, BSL and other languages to ensure accessibility | Assigned | SO1a
C2 |  | We will adapt our procedures to take account of stakeholder views and engender trust in the way that we work |  | SO1b
i | AESC/SIO | Upgrading and updating of procedural documentation (templates, factsheets, flowcharts, checklists etc) for MSP, councillor and board member complaint handling | Assigned |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
All documentation updated, adopted and published, in the form of a draft investigations manual for consultation
Procedures adopted and staff trained on use
ii | SIO | Issue manual to key stakeholders for comment | Assigned
Draft manual published on website
Stakeholder views invited
Responses incorporated
iii | SIO | Reintroduce previous KPIs and consult on these and other new ones to track progress of investigatory work. | Assigned
Reintroduce prior KPIs by reference to annual reports
Design new KPIs related to stakeholder views on our performance
Consult stakeholders on appropriateness and relevance
Analyse responses and adapt KPIs as appropriate
|  | Put tracking measures in place and assess for efficacy/accuracy | [9 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  | Report on progress internally against KPIs quarterly and externally annually | [9 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
iv | SIO | Stay up to date with case and legislative developments in ethical standards framework across UK (then integrate as standing agenda item in IO meetings) |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
C3 |  | We will pubish our procedures as revised so that everyone knows what to expect |  | SO1c
i | SIO | Publish revised investigations manual | Assigned
| SIO | Reviwing and updating investigations manual
ii | HCS/CST | Have parts of manual that are of interest and relevance to the public translated into BSL, Easy Read and other languages
C4 |  | We will highlight the need for the provision of support for complainers, respondents and witnesses in cases in which we are investigating complaints about bullying and harassment, including sexual harassment |  | SO1e
Consult key stakeholders on what support might look like.
Identify sources of support
Signpost support on templates and websites
Public Appointments
A1 |  | We will assist with the implementation of the revised Code of Practice for appointments with a greater focus on outcomes, accountability and transparency and an emphasis on learning lessons | Assigned | New SO?
i | HCS/CST | Have parts of Code that are of interest and relevance to the public translated into BSL, Easy Read and other languages
A2 |  | We will provide guidance and support to everyone engaged in the appointments process with a view to their implementing the new Code's provisions effectively |  | SO2d
i | AESC/PAM | Draft statutory guidance | Assigned
Publish statutory guidance
ii | AESC/PAM | Run training and review training developed by SG for all relevant stakeholders on new Code's application | Assigned
iii | AESC | New Code comes into effect | Assigned
Continual training and guidance developed to support revised Code
A3 |  | We will report publicly on the difference that the new Code of Practice is making to the appointments process, for good or bad, with a view to improving on practices. We will do so by publicising instances of good practice or innovative practice and learning as well as areas for improvement |  | SO3b
i | AESC | Engage with the Scottish Parliament's subject committee about appointments practices with a view to making improvements and increasing transparency | Assigned
Agree suitable reporting arrangements
Following discussion, submit periodic reports
ii | APAM | Publish good practice case studies on website | Assigned |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
iii | APAM | Continue to feed into lessons learned for the Scottish Government by seeking applicant and panel member views | Assigned |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  | Run applicant surveys on a round by round basis and provide a feedback report, whenever a request to run a survey is made. |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  | Survey panel chairs (and body chairs where appropriate) at the end of appointment rounds to seek their views on PAA performance and the PA process. |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
A4 |  | We will seek support to revise and republish Diversity Delivers to include new recommendations for the achievement of greater board diversity | Assigned | SO2b
| AESC | Consult informally from October 2023
| AESC | Run formal consultation from June 2024
| AESC/PAM | Commence research into good practice and what the content of the revised strategy should include
Governance and Accountability
G1 |  | We will put new and more effective governance measures in place, inclusive of independent elements, to ensure for ourselves and to assure others, by way of public reporting, that we are achieving our objectives in line with our purpose and our values and in line with the resources made available to us |  | Mission Statement above SO3
i | AESC/SMT | Full review of governance arrangements | Assigned
Agree three year plan with internal auditor
Review of Advisory Audit Board remit and membership
Review of whistle-blowing policy
ii | AESC/AO | Engage with SPCB to assess and fully implement external governance arrangements and address Commissioner funding issues | Assigned |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
iii | AESC/SMT | Maintain SMT meetings | Assigned |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
iv | AESC/AO | Adhere to arrangements for risk assessment | Assigned |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
v | AESC/SIO | Commission an external independent review of all decisions made on complaints from August 2020. Report on findings | Assigned
Seek legal advice on competency of such a review
Subject to legal advice seek approval for contingency funding for review
|  | Subject to legal advice and funding commission review | [11 empty] | ?
|  | Report on findings if review conducted. | [19 empty] | ?
vi | AESC/AO | Review schemes of delegation to incorporate results of workforce planning | Assigned
vii | AESC/SMT/SPCB | Consider whether standing orders can be revised to ensure collaborative decision making between ESC/SMT and wider organisation and preclude management override of controls | Assigned
Revise standing orders to give SMT a clear governance role set out in terms of reference for ESC and SMT members
Ensure ESC bound by SMT decisions in legislation and/or by some other contractual means
viii | AO/AESC/SMT | Continue to operate the revised budget process to ensure formal approval obtained from SMT as a whole on an annual rolling basis including recommending the budget for submission to the SPCB | Assigned
ix | AESC/AO | Prepare a medium-term financial plan to include alternative scenarios of expected income and expenditure in future years, associated assumptions for each scenario and quantifying the funding gaps. Take account of the impact of leaving the EU, the Covid-19 pandemic and other expected changes | Assigned
Consider whether a medium-term financial plan is required or of benefit.
Draft financial plan showing variances by scenario(s) and their potential impact on the office's ability to fulfil its functions
G2 |  | We wil adopt quality assurance monitoring of key performance indicators, such as timescales for investigation stages, including surveys of the views of those with whom we come into contact, and report publicly on the results. We will use those results to improve on what we do and ensure our practices are equitable |  | SO3a
i | AESC | Update performance management framework to take account of risks. | Assigned
ii | AESC/SMT | Agree organisation-wide KPIs and how to monitor these | Assigned
iii | PAM/SIO | Include a survey that both complainers and respondents can complete on an anonymous basis to give views on how we investigate complaints | Assigned
Design and roll out survey
Set baseline based on initial results
G3 |  | We will work in partnership with the Scottish Government, the Scottish Parliament, the Standards Commission for Scotland and other stakeholders to promote good practice and to ensure that lessons are learned from the outcomes of our investigations. Our ongoing engagement with our stakeholders will be regular and meaningful. |  | SO3c | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Other Corporate activity
O1 |  | We recognise that public sector resources are limited and understand that we must review, scrutinise and report publicly on our work to ensure best value and continous improvement |  | Comment under Costs
i | AESC/AO | Draft biennial business plan for 2022-24 | Assigned
Draft plan
Publish plan
|  | Consider biennial plan on an ongoing basis to include the following year | [5 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
ii | HCS | Publish Annual Report and Accounts | Assigned
Prepare ARA
Issue draft ARA
Populate online ARA template
iii | AESC/SMT | Decision on office accomodation needs | Assigned
Further survey on staff flexible working preferences
Assess current and predicted use of office accommodation
Identify solution that meets both staff and business needs
Maintain existing accommodation or move to new model
iv | AESC/HCS | Review contractual and practical arrangements for CMS | Assigned
CMS user feedback session
Analysis of feedback to identify 'quick fixes' with current system and longer term requirement
Identify alternatives such as CMS upgrade or replacement
Decide on preferred option
Procure new solution
v | AO | Risk assessment of EU exit on current and future activities | Assigned
vi | HCS | Review of records management arrangements in prepartion for resubmission of our RMP to NRS | Assigned
vii | AO/PAM | Review and revise all outstanding policies that are currently beyond their published review date | Assigned
viii | AO | Review entire website to ensure up to date - see project plan | Assigned |  |  |  | - | - | - | - | - | - | - | - | -
ix | AO | Review and maintain entire website and ensure pages and publications are up to date on a rolling basis
x | HCS | Tender for IT Managed Service Provider | Assigned
xi | HCS | Tender for website developer and hosting services | Assigned
xii | HCS | Investigate transfer to cloud-based server and records management | Assigned
xiii | SMT | Induct new Commissioner in relation to all functions | Assigned
Note on E3: Karen Elder: 'Actions under this heading are set out in page 18 of this plan.' They're not.
Note on E38: Karen Elder: 'Actions under this heading are set out in page 18 of this plan.' They're not.
Note on E46: Karen Elder: 'Actions under this heading are set out in page 18 of this plan.' They're not.